## Feuille 1
Tasks | Hours to finish | Hours spent - Day 1 | Hours spent - Day 2 | Hours spent - Day 3 | Hours spent - Day 4 | Hours spent - Day 5 | Hours spent - Day 6 | Hours spent - Day 7 | Hours spent
5. Accounts | 35 | 0 | 10 | 0 | 0 | 5 | 10 | 10 | 35
Actual remaining hours | 35 | 35 | 25 | 25 | 25 | 20 | 10 | 0
Estimated remaining hours | 35 | 30 | 25 | 20 | 15 | 10 | 5 | 0