## Feuille 1
Tasks | Hours to finish | Hours spent - Day 1 | Hours spent - Day 2 | Hours spent - Day 3 | Hours spent - Day 4 | Hours spent - Day 5 | Hours spent - Day 6 | Hours spent - Day 7 | Hours spent - Day 8 | Hours spent - Day 9 | Hours spent - Day 10 | Hours spent - Day 11 | Hours spent - Day 12 | Hours spent - Day 13 | Hours spent - Day 14
5. Accounts | 70 | 0 | 10 | 0 | 0 | 5 | 10 | 10 | 5 | 10 | 5 | 0 | 0 | 5 | 10 | 70
Actual remaining hours | 70 | 70 | 60 | 60 | 60 | 55 | 45 | 35 | 30 | 20 | 15 | 15 | 15 | 10 | 0 | 70
Estimated remaining hours | 70 | 65 | 60 | 55 | 50 | 45 | 40 | 35 | 30 | 25 | 20 | 15 | 10 | 5 | 0